**Scope and Quotation for Power BI   
KPI Dashboard and Microsite Development**

**Client:** Malaysia Petroleum Resources Corporation (MPRC)  
**Project:** KPI Dashboard and Microsite Development  
**Date:** July 9, 2025

**1. Project Overview**

The aim of this project is to create an interactive Power BI KPI dashboard to visualize key performance indicators, sourced initially from Excel files in SharePoint. This dashboard will then be embedded into a dedicated microsite, providing easy access and a streamlined user experience for Malaysia Petroleum Resources Corporation.

**2. Scope of Work**

**Phase 1: Data Preparation & Modeling (Power BI)**

**Data Source Integration:**

* Connecting Power BI to multiple Excel files stored in SharePoint
* Initial assessment of Excel file structures and data quality
* Data cleaning, transformation, and shaping using Power Query (e.g., handling missing values, data type conversions, unpivoting)

**Data Modeling:**

* Establishing relationships between different data tables
* Creating calculated columns and measures (DAX) to derive key metrics and insights
* Optimizing the data model for performance and ease of use

**Phase 2: Power BI Dashboard Development**

**Dashboard Design & Visualization:**

* Designing an intuitive and visually appealing Power BI dashboard layout
* Creating relevant charts, graphs, tables, and KPIs to represent key data points
* Implementing interactive elements (e.g., filters, slicers, drill-through capabilities) for in-depth analysis
* Ensuring responsiveness for different screen sizes (desktop, tablet)

**Reporting & Iteration:**

* Developing 1-3 key report pages based on initial requirements (Number of pages can be adjusted based on detailed requirements)
* Up to 2 rounds of revisions based on client feedback

**Power BI Service Publishing:**

* Publishing the developed dashboard to the Power BI Service

**Phase 3: Microsite Development & Integration**

**Microsite Setup:**

* Creation of a simple, static microsite (e.g., using HTML/CSS/JavaScript or a lightweight CMS like WordPress for a single page/few pages)
* Basic design and branding integration (client logo, color scheme)
* Domain and hosting setup (if required and not already provided by client - annual costs for these are separate)

**Power BI Embedding:**

* Securely embedding the Power BI dashboard into the microsite
* Ensuring seamless user experience and proper display
* Implementing necessary authentication/authorization if required (assuming Power BI Pro user access will be managed within Power BI Service)

**Phase 4: Testing & Deployment**

**User Acceptance Testing (UAT):**

* Facilitating client UAT to ensure the dashboard and microsite meet expectations

**Deployment:**

* Final deployment of the microsite and Power BI dashboard

**Handover & Basic Training:**

* Providing documentation on data refresh process and basic usage of the dashboard
* One session of basic training for relevant users (e.g., Power BI Service navigation, dashboard interaction)

**3. Out of Scope**

* Complex data warehouse development
* Integration with systems other than SharePoint Excel files
* Advanced custom visuals requiring significant development
* Ongoing data entry or data cleansing beyond initial setup
* Extensive user management or security configurations beyond standard Power BI Service sharing
* Advanced features for the microsite (e.g., e-commerce, user logins for the microsite itself, complex forms, backend databases for the microsite)
* SEO optimization for the microsite beyond basic setup
* Content creation for the microsite (text, images - to be provided by client)
* Power BI Premium capacity licensing

**4. Quotation**

**A. Service Fees**

| **Item** | **Description** | **Estimated Effort  (Man-days)** | **Rate (RM/day)** | **Total (RM)** |
| --- | --- | --- | --- | --- |
| **Power BI Development** | | | | |
| Data Preparation & Modeling | Initial data assessment, cleaning, transformation (Power Query), data modeling (DAX) | 6.5 | 990 | 6,435 |
| Dashboard Design & Visualization | Creating interactive visuals, layout, slicers, drill-through  (For 1-3 reports) | 5 | 990 | 4,950 |
| **Microsite Development** | | | | |
| Microsite Setup & Design | Simple HTML/CSS/JS or lightweight CMS setup, basic branding (1-3 pages) | 4 | 880 | 3,520 |
| Power BI Embedding & Integration | Secure embedding, ensuring responsiveness | 1.5 | 880 | 1,320 |
| **Project Management & QA** | | | | |
| Project Management | Communication, planning, coordination | 2.5 | 935 | 2,337.50 |
| Testing, Deployment & Training | UAT, final deployment | 1.5 | 935 | 1,402.50 |
| **Sub-total for Services** | | **21 man-days** |  | **RM 19,965** |
| **B. Licenses & Subscriptions** | | | | |
| **Power BI Pro Licenses** *(will be managed by the client)* | |  | - | 0 |
| **Microsite Hosting & Domain** | |  | prorated | 110.00 |
| **Total Estimated Cost** | | | | **RM 20,075** |

**B. Licenses & Subscriptions**

**Power BI Pro Licenses:**

* Cost per user/month (starting April 1, 2025): USD 14.00 (approx. RM 66.00 based on current exchange rate 1 USD = 4.70 MYR)
* 2 users for 6 months: 2 users × 6 months × RM 66.00/user/month = RM 792.00

**Microsite Hosting & Domain (if required and not provided by client):**

* Domain Name (.com / .my): RM 60 - RM 120 per year
* Shared Hosting: RM 100 - RM 600+ per year
* Estimated Microsite Hosting & Domain (6 months prorated): RM 110.00

**5. Payment Schedule**

* **Upfront Payment:**   
  30% upon signing the agreement (RM 6,260.10)
* **Milestone 1 Completion:**   
  60% upon Power BI Dashboard development completion and Microsite development and Power BI embedding completion (RM 12,520.2)
* **Final Payment:**   
  10% upon project completion and handover (RM 2,086.70)

**6. Timeline**

The estimated timeline for this project, from initiation to deployment, is approximately   
**4-6 weeks**, depending on the complexity of data and responsiveness for feedback.

**7. Assumptions & Next Steps**

**Assumptions:**

* All required Excel data files are accessible from SharePoint and contain consistent data structures
* Client will provide necessary access to SharePoint, Power BI tenant, and any other relevant systems
* Client will provide timely feedback and content (e.g., branding guidelines, specific text for microsite) during all project phases
* The scope of reports and dashboard complexity is limited to 1-3 key pages with standard Power BI visuals
* Microsite is a simple, static site primarily for embedding the Power BI dashboard, without complex backend integrations or user authentication beyond Power BI itself
* Power BI Pro licenses are assumed to be managed by the client or acquired through this quotation

**Next Steps:**

1. Detailed discussion to refine requirements and data sources
2. Finalization of the exact number of reports/dashboards and microsite pages
3. Formal agreement and contract signing

**Please note:** This is an estimated quotation. A more precise quote can be provided after a detailed requirements gathering session and a review of the actual data complexity and desired dashboard/microsite features.

**Prepared By:**  
Ahmad Najmi bin Ariffin, MyKetapang Group  
[myketapang@gmail.com](mailto:myketapang@gmail.com)  
0134748674  
July 9, 2025